## Slide 1
POST-MERGER INTEGRATION
PMI Plan: Key Phases & Synergy Tracking
Ensure business continuity, secure key talent, and establish immediate communication channels.
Integrate core operational systems, standardize processes, and align IT infrastructure.
Asuccessful integration requires astructuredapproach,focusingonstabilization,systemsalignment,andcommercial
integration to unlock full synergy potential.
Merge sales, marketing, and customer support functions to optimize market reach and client engagement.
1
2
3
Month 1-2: Stabilize
Month 3-4: Systems
Month 5-6: Commercial Integration

## Slide 2
Tracking Synergy Realization
Cost Savings
Revenue Growth Operational Efficiency Market Share
15% Reduction
10% Increase 20% Improvement 5% Expansion
3% Achieved
2% Achieved 5% Achieved 1% Achieved
8% Achieved
5% Achieved 12% Achieved 2.5% Achieved
Regular monitoring and reporting will highlight progress and allow for timely adjustments to integration strategies.
Quantifiablemetricswilldriveaccountabilityandensurethatexpectedsynergies translate into tangible value post-acquisition.
Synergy Type
Target (12 Months)
Q1 Status
Q2 Status

## Slide 3
RISK ASSESSMENT
Key Risks & Mitigation Strategies
Integration exceeds 6-month window
Founders exit
despite retention
clause Synergies don't
materialize in 12
months Key client
concentration at
target Overpayment /
Valuation risk
Post-acquisition
margin dilution
Low
Low
High
Medium
Medium
Medium
High
High
High
High
Medium
Medium
Addressingpotentialchallengesproactivelyiscriticalforsafeguardingtheinvestmentand ensuring a smooth transition.
Dedicated PMI team, clear milestones, external integration consultants, agile project management.
Enhanced golden handcuffs, performance incentives,
structured handover process, strong internal succession
planning. Rigorous synergy tracking, cross-functional accountability,
regular review meetings, contingency plans for
underperforming areas. Diversification strategy post-acquisition, relationship
management overlap, contract review and renegotiation,
value proposition enhancement. Thorough due diligence, multiple valuation models, earn-
out structures linked to performance, expert third-party
review. Cost optimization initiatives, pricing strategy review,
operational efficiency improvements, economies of scale
leveraging.
Risk
Probability
Impact
Mitigation Strategy

## Slide 4
ACQUISITION OUTLOOK
Final Recommendation
The target provides immediate
access to a rapidly growing market
segment, accelerating our strategic
objectives.
Integration promises significant operational efficiencies and expanded customer offerings, enhancing competitive advantage.
Approval is contingent upon successful negotiation of earn-out provisions, retention of key founders for a minimum of 3 years, and integration cost adherence within 10% of projected budget.
Acquisition includes key human
capital and proprietary
technologies that will drive future
innovation.
Basedon comprehensiveduediligenceandstrategicalignment, the acquisition presents a compelling opportunity for market
expansion andvaluecreation.
Strategic Market Entry
Synergistic Value Proposition
Strengthened Talent & IP
ACQUIRE ✅